## Sheet1
Task | Description | Start | End | Duration (weeks)
Milestone 1: Research Proposal | Background, Problem Statement, Literature review, etc. | 2025-07-21 | 2025-08-17 | 4
Week 1 | Background, Problem Statement, Literature review, Hypothesis formulation, Clarifications | 2025-07-21 | 2025-07-27 | 1
Week 2 | Finalize research questions, Aims and Objectives, Significance, Scope, Clarifications | 2025-07-28 | 2025-08-03 | 1
Week 3 | Research Methodology, Resources, Evaluation metrics, Clarifications | 2025-08-04 | 2025-08-10 | 1
Week 4 | Title, Research plan, References, Proposal template, Supervisor sign-off, Submit | 2025-08-11 | 2025-08-17 | 1
Milestone 2: Interim Report | Design, Data collection, Model setup, Architecture, Reporting | 2025-08-25 | 2025-10-05 | 6
Week 5 | Literature review, Design & Data collection | 2025-08-25 | 2025-08-31 | 1
Week 6 | NER model decision, Define PII categories, Setup, Pre-processing | 2025-09-01 | 2025-09-07 | 1
Week 7 | Plan architecture integration, Create diagrams | 2025-09-08 | 2025-09-14 | 1
Week 8 | Code setup, LLM subscriptions, Key component experiments | 2025-09-15 | 2025-09-21 | 1
Week 9 | Experimental results, Write Interim report, Supervisor review | 2025-09-22 | 2025-09-28 | 1
Week 10 | Refine and submit Interim report | 2025-09-29 | 2025-10-01 | 1
Milestone 3: Final Thesis & Video | Analysis, Modeling, Evaluation, Writing, Submission | 2025-10-13 | 2025-12-07 | 8
Week 11 | Literature review, Data analysis and interpretation | 2025-10-13 | 2025-10-19 | 1
Week 12 | Train/fine-tune NER model, Impact statement, Refine results, Supervisor clarifications | 2025-10-20 | 2025-10-26 | 1
Week 13 | Refine evaluation metrics, Propose best architecture | 2025-10-27 | 2025-11-02 | 1
Week 14 | Write and disseminate findings, Supervisor clarifications | 2025-11-03 | 2025-11-09 | 1
Week 15 | Write and disseminate findings | 2025-11-10 | 2025-11-16 | 1
Week 16 | Discussion, Future work, Writing, Supervisor clarifications | 2025-11-17 | 2025-11-23 | 1
Week 17 | Review final report, Prepare video | 2025-11-24 | 2025-11-30 | 1
Week 18 | Refine final report, Supervisor sign-off, Submit final report and video | 2025-12-01 | 2025-12-01 | 1